## Sheet1
# | Issue | Error Code/problem details | Comments Fix Action | Date Found | Date Fixed
1 | Game will not Start | Assets/AstarPathfindingProject/Generators/NavMeshGenerator.cs(xxx,4): error CS0103: The name `Profiler' does not exist in the current context | Error was cause by a major update to Unity, changed namespace to UnityEngine.Profiling in all code references | 2017-01-18 | 2017-02-22
2 | Multiple errors for obsolete scripts | Assets/Standard Assets/2D/Scripts/Restarter.cs(12,51): warning CS0618: `UnityEngine.Application.loadedLevelName' is obsolete: `Use SceneManager to determine what scenes have been loaded' (example 1 of Many) | Moved to more updated scripts using SceneManager | 2017-01-18 | 2017-02-22
3 | Fast forward button operates incorrectly | FF button does not toggle on/off and stays lit. | Fixed toggle and lighting scheme of FF button | 2017-01-18 | 2017-02-22
4 | Errors with Tutorial botton | Many hard coded references to a tutorial button that is non-functional within the game at this time. | Created a placeholder until code can be cleaned up | 2017-01-18 | 2017-02-22
5 | Lag interfering heavily with UI | Whenever the game is started or paused and the user attempts to place a piece into play there is a tremendous lag and the piece trails behind the users finger or mouse. | Removed a call to DrawCircle within 'CircleEdgeCollider2' that would make a call every clock cycle and perform physics calculations severly hindering gameplay | 2017-01-18 | 2017-02-22
6 | Entire play area can be moved around on the IPAD | Player can "grab" entire play area and move it around on IPAD | Made canvas and several other scripts children under Main Camera. Had to go into the script and change the parent. | 2017-01-18 | 2017-04-20
7 | Most of the coding has no comments | Hard for the current group to get started with coding issues, it will also be difficult for subsequent groups to understand how to start or correct any errors. | Comment code | 2017-01-18 | 2017-04-26
8 | G-Protein behaving erratically preventing a win | G-Protein will not remain in place on receptor and await GTP. It "flies" out of the cell and prevents any chance of winning the game. | Changed Rigidbody2D settings. Changed G-Protein script ‘G_ProteinCmdCtrl’. Notes added to code. | 2017-03-02 | 2017-03-10
9 | Project hierarchy poorly factored | Hard to find sprites and scenes | Created a new Assets folder called ‘Scenes’ which contains all the scenes for the game. Moved all scenes and sprites into their own folders inside the Assets folder | 2017-03-02 | 2017-03-10
10 | No scene for Level 2 | Needed a scene to begin work on level 2 | Created scene for level 2 | 2017-03-02 | 2017-03-10
11 | No prefabs for cell structures on level 2 | No pieces for the cell structures requested by Dr. Cline. | Created prefabs and added new scripts to get desired functionality for the new pieces. | 2017-03-02 | 2017-03-25
12 | No change log | No change log has been created to document major changes and additions to the game | Create change log | 2017-03-02 | 2017-03-18
13 | No issue log | No running issue log to note issues the group has had | Create Issue log | 2017-03-02 | 2017-03-25
14 | Nuclear Pore not centered on nucleus when snapped into place | Hinders immersion and represents lack of attention to detail | Recenter Nuclear pore | 2017-03-03
15 | Congratulations screen not displaying correctly | Layering appears to be incorrect | Review setting within unity | 2017-03-03 | 2017-04-20
16 | Signalling molecule disappearing when binding to receptor | MissingReferenceException: The variable _ActiveReceptor of receptorScript doesn't exist anymore. | Refactored receptor scripts to change the way the receptor functions. | 2017-03-03 | 2017-03-12
17 | Receptor flies off of nuclear membrane in level 2 | When placing a receptor side in level two if a piece is placed on the cell membrane, which is an allowable error, when a signalling protein is placed into a right receptor the pieces will track to each other causing the right receptor to leave the cell membrane. | Review scripts to determine fix action | 2017-03-03
18 | Menu options no longer reflect accurately | The menu options do not allow you to move direct to level 1 or 2 respectively | Updated menu options in unity | 2017-03-13 | 2017-03-13
19 | Reload scene always loads level two | When reload scene is clicked it loads level 2 even when in level 1 | Remove hard coding that calls the scene for level 2 | 2017-04-13 | 2017-04-16
20 | Level 2 auto-wins | After winning level 1 level 2 automatically loads in a win state | Re-named scene (‘ReloadScene’) to ‘LoadScene’ and refactored the script to allow for new scenes to load and current scenes to refresh on button click. | 2017-04-13 | 2017-04-16
21